##### Beyond the Net Programme Medium and Large Funding

##### Timeline September Cycle 2016

|  |  |  |
| --- | --- | --- |
| **Activity** | **Timeline**  | **Who** |
| Info Session | July … | Ilda |
| Deadline | 15 Sept 2016 | Ilda |
| Pre-screening & Chapter Dev Team Review | 16 Sept to – 6 Oct | Ilda & Chapter Team |
| Q & A Applicants & others based Feedback | 16 Sept to – 6 Oct 8 | Ilda & Applicants |
| Committee Review /Score /$ Vote | 10 to 24 Oct  | Selection Committee |
| Q & A Applicants & Experts Evaluation if required | 24 to 31 Oct | Ilda & Applicants |
| Committee Final vote and Online meeting | 04 Nov (TBC) | Selection Committee (Ilda)(invite Lia/Nikki) |
|  |  |  |
| Applicants Notifications  | 7 -11 Nov | Ilda |
| Blog article | 7-11 Nov | Ilda + Nikki |
| Public Announcements | Week of the 21st  | Ilda + Lia |
|  |  |  |
|  |  |  |
|  |  |  |